## Slide 1
Product Release Plan
IPSEN PROJECT
March - June 2026

## Slide 2
Project Overview
📅
14 Weeks
Total Timeline
🚀
3 Releases
7 Sprints
👥
2 Pods
Cross-functional
⚡
160 SP/Sprint
Total Capacity
Start Date: 2 March 2026 | Sprint Duration: 2 Weeks

## Slide 3
Team Capacity
Pod 1
4 AI Backend + 2 Frontend
96 SP Backend | 32 SP Frontend
Pod 2
2 AI Backend + 2 Frontend
32 SP Backend | 32 SP Frontend
Total Capacity per Sprint
96 BE SP + 64 FE SP = 160 Total SP

## Slide 4
Release 1
Platform Foundation & Core System
6 Weeks | 3 Sprints
2 March – 10 April 2026
Sprint 1
2-13 Mar
Infrastructure & Core Setup
Sprint 2
16-27 Mar
Knowledge Backbone & Governance
Sprint 3
30 Mar-10 Apr
AI Drafting & Agentic Workflow
🎯 Goal: Internal Beta with AI Drafting Capability

## Slide 5
Release 2
Enterprise Hardening & Intelligence
4 Weeks | 2 Sprints
13 April – 8 May 2026
Sprint 4: Enterprise Hardening
• Localization Framework
• Multi-region support
• Performance optimization
• Audit Logging
Sprint 5: Governance & Workflow
• Version Control
• Feedback Loop System
• Review Workflow
• Workflow Orchestration
🎯 Goal: Enterprise-Ready System

## Slide 6
Release 3
Optimization & Analytics
4 Weeks | 2 Sprints
11 May – 5 June 2026
Sprint 6: AI Optimization
• Advanced AI Orchestration
• Content Scoring Framework
• Quality Metrics
Sprint 7: Analytics & Intelligence
• Analytics Dashboard
• Usage Metrics
• Auto-approval Layers
• Admin Insights
🎯 Goal: Production Excellence & Automation

## Slide 7
Project Timeline
Release 1
6 weeks
2 Mar – 10 Apr
Release 2
4 weeks
13 Apr – 8 May
Release 3
4 weeks
11 May – 5 Jun
14 Weeks Total • March – June 2026