## Overview
Product Release Plan - Ipsen
Project Start: 2 March 2026 ¦ Sprint Duration: 2 Weeks
Pod Configuration
Pod | Backend Engineers | Frontend Engineers | Backend Capacity (SP/Sprint) | Frontend Capacity (SP/Sprint) | Total Capacity (SP/Sprint)
Pod 1 | 4 | 2
Pod 2 | 2 | 2
Total
Release Timeline
Release | Duration | Start Date | End Date | Sprints | Goal
Release 1 | 6 Weeks | 2-Mar-26 | 10-Apr-26 | 3 | Platform Foundation & Core System
Release 2 | 4 Weeks | 13-Apr-26 | 8-May-26 | 2 | Enterprise Hardening & Intelligence
Release 3 | 4 Weeks | 11-May-26 | 5-Jun-26 | 2 | Optimization & Analytics

## Sprint Details
Sprint Breakdown
Sprint 1 | 2-Mar-26 - 13-Mar-26
Theme: Infrastructure & Core Setup
Track | Task
Backend | Configure AWS Hosting Services
Backend | Configure Environments & Deployments
Backend | Backend Setup (BFF Layer)
Backend | SSO Login (Backend)
Backend | RBAC (Phase 1)
Backend | Brand Library (Backend)
Backend | Document Management (Backend)
Frontend | SSO Login UI
Frontend | Brand Library UI
Frontend | Document Upload UI
Frontend | Content Collection UI (Basic)
Frontend | Master Story UI (Basic Form)
Sprint 2 | 16-Mar-26 - 27-Mar-26
Theme: Knowledge Backbone & Governance
Track | Task
Backend | Complete RBAC
Backend | Knowledge Base – Ingestion Workflow
Backend | Content Collection Backend
Backend | Master Story Completion
Backend | Dynamic Template Framework (Basic)
Frontend | Knowledge Base UI
Frontend | RBAC Admin UI
Frontend | Dynamic Template UI (Basic)
Frontend | Master Story Enhancements
Sprint 3 | 30-Mar-26 - 10-Apr-26
Theme: AI Drafting & Agentic Workflow
Track | Task
Backend | Agentic Framework
Backend | Text Generation Agents (Core)
Backend | Agentic Drafting Workflow
Backend | Template Binding Logic
Backend | Draft Storage System
Frontend | Drafting UI
Frontend | Template Selection UI
Frontend | Document Preview
Frontend | Edit & Regenerate Controls
Sprint 4 | 13-Apr-26 - 24-Apr-26
Theme: Enterprise Hardening
Track | Task
Backend | Localization Framework
Backend | Multi-region support
Backend | Performance optimization
Backend | Prompt refinement
Backend | Audit Logging
Sprint 5 | 27-Apr-26 - 8-May-26
Theme: Governance & Workflow
Track | Task
Backend | Version Control
Backend | Feedback Loop System
Backend | Review Workflow
Backend | Workflow Orchestration Improvements
Sprint 6 | 11-May-26 - 22-May-26
Theme: AI Optimization
Track | Task
Backend | Advanced AI Orchestration
Backend | Content Scoring Framework
Backend | Quality Metrics
Sprint 7 | 25-May-26 - 5-Jun-26
Theme: Analytics & Intelligence
Track | Task
Backend | Analytics Dashboard
Backend | Usage Metrics
Backend | Auto-approval Layers
Frontend | Admin Insights